**4th Steering Committee meeting of the ENI SEIS II East project**

**12 November 2019**

European Environment Agency, Copenhagen, Denmark

**ACTION LIST FROM THE MEETING**

| **Action** | **Timing** | **Lead** | **Comments** |
| --- | --- | --- | --- |
| **Project implementation** | | | |
|  |  |  |  |
| Share the feedback and outcome from the AQ wortkshop in Tbilisi in late November | First half of December 2019 | EEA/ Jasmina |  |
| National Focal Points/Assistants to maintain regular meetings of the SEIS National Implementation Teams, integrating also the open data roadmaps follow-up and regular update | Continuous until the end of the project | NFPs/ assistants |  |
| Ensure that the project website is kept updated with project outputs with active links to country news at national level and vice versa | Continuous until the end of the project | EEA/ Victoria | With information and support from NFPs/ assistants |
| The EEA, together with the European Commission and in dialogue with the countries, to identify a suitable setting, date and location for the final project event in spring 2020 (tbd April-May) | Dec 2019 – Jan 2020 | EEA/ Victoria |  |
| Identify areas to be highlighted for each of the partner countries at the final event and ensure higher visibility at country level | Dec 2019 | EEA/ Victoria |  |
| Consider contrinuation/finalisation of the work on Corine Land Cover (CLC) in 2020 | Dec 2019 – Jan 2020 | EEA/ Adriana |  |
| Implement CLC2000 component in Armenia and organise regional workshop to present the results by ETC ULS | Jan-June 2020 | Armenian partners and  ETC ULS |  |
| Partner countries to comment in the next 2-3 weeks on the Maturity reports on open data and e-government to be sent by EEA in week 47 | Nov-Dec 2019 | NFPs/ assistants | NFPs/assistants to ensure broad dissemination at national level for commenting  The reports can be used as reference for identifying further actions |
| The Open Data Roadmaps to be revised and updated annually, also in conjuction with reporting on progress linked to Arhus Convention and PRTR | Continuous | Partner countries |  |
| Explore ways for translating the maturity reports in national languages | In 2020 | UNECE | By approaching UNDP local offices |
| Participation in the consultation of the ENI Regional State of Water Report | Q1 2020 | EEA/ Nihat | NFPs/ assistants to ensure involvement of all relevant stakeholders |
| Organising dedicated launch events in the three Caucasus countries for the EcoPortals currently under development | Q1-Q2 2020 | EEA & NFPs/ assistants |  |
| The EEA together with the Slovak Environmental Agency (SEA) to further support the country experts on SOER production (consulation online), integrated thematic assessments, regional assessment and updated Country Briefings | Q1-Q2 2020 | EEA/  Jana | NFPs/ assistants to ensure involvement of all relevant stakeholders |
| Update availability of the UNECE environmental indicators and assessments online | Q1 2020 | EEA/  Jana/  Victoria | With support by NFPs/ assistants |
| Consider continuation of activites on SEEA with self-assessment of SEEA progress and SEEA land country fiche | Q1-Q2 2020 | EEA/  Jana | NFPs/ assistants |
| Consider organising an EEAcademy Summer School on Integrated Assessments and the EEA SOER 2020 | Q2 2020 | EEA/ Jana | Exact timing to be confirmed |

|  |  |  |  |
| --- | --- | --- | --- |
| **Synergies and partnerships** | | | |
|  |  |  |  |
| Maintiain regular dialogue with the EU Delegations in each country on implementation of project activities and visibility of results vis-a-vis other projects/inititaives | Continuous | EEA, EC & countries |  |
| Maintain close cooperation with relevant partners, ensuring also continuation and sustainability of project outcomes/results | Continuous until the end of the project | EEA & countries |  |
| Support to relevant UNECE working groups and feeding the project results into preparation for the next pan-European assessment process | Q1-Q2 2020 | EEA | Support to be provided within the project timeframe (by 31 July 2020) |
| EEA to ensure translation of the SOER2020 Executive Summary in Russian language | Dec 2019 | EEA with ZOI support | For wider dissemination of the SOER2020 in support of the above action |