## Foglio1
Activity | Sub-activity | 2017 |  |  | 2018 |  |  | 2019 |  |  | Remarks | Output
|  | I | II | III | I | II | III | I | II | III
1. Identification of the state of national database infrastructure for SDI and data managenment
| Definition and distribution of online survey (published on an Infomap wepage, translated in French and English) for the identification of national databases and state of the SDI. One invitation will be send by email to a mailing list of national NFPs. The survey will be based on: type of datasources (GIS or analytical format), specifics thematic issues linked to H2020 indicators, owner, data policy access, level of interoperability (web services, download, other methods of delivery), spatial and temporal coverage, etc. | [9 empty] | The tranlsation is in charge of EEA. Support to country (EEA) will be crucial in this phase. | 1. list of databases and GIS layers inline with the indicators.
| Elaboration of answers produced by the online survey to produce a list of specific databases and GIS layers on which information will be collected to generate the catalogue of metada. Geonetwork (catalogue of metada already in use by INFORAC in the context of INFO MAP infrastructure) for all data. | [10 empty] | 2. catalogue of metadata
2. Set up of Info map for new data reporting
For the selected ECAP indicators (monitoring data flows implemented in EcapMed II project) n°13, 17, 22 on nutrients, contaminants and marine litter definition of XML schema and data dictionary for monitoring data.
| Identification and revision of XML schema for monitoring data flows on waste, waste water treatment (Urban Waste Water Treatment Directive questionaires), release of toxic substances (PRTR). | [10 empty] | 1. New data monitoring data flows infrastructure on INFO MAP for waste, urban waste water and toxic
Revision and adjustments to the regional data infrastructure for the implementation of monitoring data flows for the new data reporting on waste, waste water treatment, release of toxic substances (PRTR).
implementation of software procedures for calculation of H2020 indicators once the metrics and spatial/temporal aggregation rules are defined (according to WP2/WP3 outputs)
3. Development of data policy documents at country level, in support of common regional standards | Analysis of metadata catalogue's information (point n°1) to give specific indications on data policy for a better implementation of H2020 indicators (access, sharing, re-use) | [10 empty] | suggestions listed in a document
4. SDI initiated and developped at country level
| Implementation of SDI plateform (Geoviewer, geonetework or catalogue, geoserver for data services/sharing (wms, wfs)). Software as service for each country into INfoMAP for the publication, editing, sharing and connection to existing information systems based on OGC. users will be profiled according to data policy. | [10 empty] | SDI platforms
| Providing guidelines on using SDI and reporting infrastructure | [10 empty] | Guidelines
| Training of national experts to use SDI and reporting infrastructure. Two Workshops at regional level (starting of activities and follow up) and trainings at country based on needs and with the possibility to provide webinars (INFO RAC e-learning platform). | [10 empty] | Trainings and helpdesk services
Customisation and integration of citizen science application "i naturalist" into INFO MAP plateform
| Development and publication of information layers with results of H2020 indicators according to WP2-WP3 outputs. | [10 empty] | Information layers
5. Extension of Medpol info system to include marine litter H2020 indicators | Extension of MEDPOL data model to include marine litter monitoring data flows in sinergy with ECAP monitoring data flow. | [9 empty] | This activity is subordinated to marine litter H2020 operational definition (WP2). Factsheets and definition.
6. Provision of training of national experts | [10 empty] | See activity n°4