## Tabelle1
Guidance for selection of activities
N° | Title of the activity | Short description of the activity | State of play initial situation | Expected outcomes from the activity – landing situation | key milestones of the activity | Links with national priorities /plans (including NAPs, and obligations toward Barcelona Conventions)/strategies - How the activity is contributing the existing national plans and obligations | Links with the project – how the activity contributes to the expected Results of SEIS II (R1, R2, R3, R4) | Links with H2020 Programme of work 2015-2020 - how this activity contributes to achieving the H2020 objectives (as specified in the H2020 work plan table) | SEIS pillars- to which SEIS pillar the activity contribute | Responsible entities for the implementation of the activity | Period of implementation | Resources for implementation -internal, internal with ENIS support, internal with other external project support, external (fully covered by another funding), etc | Links with other activities of the plan – indicate here if this activity is linked/dependant from the execution / development of another activity (e.g. a Capacity building activity implemented under SWIM/H2020 SM, EcAP MED II activity or other project/twinning/taeix)? | Sustainability
1 | SEIS/SoER/Indicators/ NlS-RIS | National Committee for SEIS are established but need to be ubdated by adding more relevant authoritiesand stakeholders such as EIF/EC&SD office/ EPAP (I, II &III project)/MoP/MoT /Acadamia | facilitate data echange/ finalize the project WP / discuss emerging issues /monitor the progress/ participate in the preparation of national reports. | establish SEIS working groups/units in each organization | communication/sustainability/committments |  | R1 : H2020 indicators is established, R2: data sharing is manged, R3: The infrastructure report offered by EEA & UNEP MAPare widly used, R4: indicators for H2020 reports are produced | protocals signed to enhance data sharing and production of indicators, sustainability, and integration | cooperation on the national level, infrastructure & content | EEAA, CAPMAS | 2017-2020 | government (internal) | linked to H2020 and SEIS | support desigion taken and policies update on the national level
2 | NAP/ NSSD (vision-plans for 2030) | NAP reviewed to be in lined with the NSSD 2030 | NAP reviewed to be in lined with the NSSD 2030 | integration of the NAPs | ensure sustainability |  | R2: data sharing |  | cooperation on the national level & content | EEAA, CAPMAS, MoP | 2017-2019 | government (internal) | linked to NAP update &NSSD | integration and sustainability
3 | Water/ Marine/ National Legistlations/ international Commitments | Coastal area chapter in the Environmental law revise and undate according to the international signed convention such as BC, MARPOL…etc, International expert needed, National consultant, 3 national workshops, 2 regional workshops | update laws to be in line with the international commitmments | Updated env. Law no 4 for the year 1994 modified by law number 9 for the year 2009 | Capacity building needed | support NAP update through updated legistlations/policies | cross cutting issue | suport the implementation of international commetiment/conventions with regard to protection of marine environment | cooperation on the national level &content | EEAA | 2017-2018 | government (internal) | linked to all international conventions
4 | water (marine)/coastal/ offshore/ports/MLMP | updating national coastal water programme to comply with IMAP, takle new subjects such as MLMP &consider sea based pollution sources, | lack of MLMP/information/cooperation | establish MLWP/WG/Database | Lack of coordination and Public participation
5 | waste water/tratment/data | establish waste water treatment database. | protect marine environmnt from land based sources pollution | data base support the poduction of indicators | lack of cooperation | achieve SDGs |  | H2020 1,2,4 | cooperation, Infrastructure, content | EEAA, CAPMAS & MOH | 2017-2018 | National/ technical support | BC/LBSP/H2020/SEIS II | Continous cooperation
6 | Water Accounts/ statistics | [7 empty] | cooperation, Infrastructure, content | MoE- WMRA/ CAPMAS/ MoLD
7 | calculation of solid waste generation (lower and higher income)/ urban and ruler areas | Study visit, TA and 3 workshops activities to cover 3 geographical areas |  | exchange of experience and methodology | [5 empty] | MoE/ WMA/ CAPMAS/ MoLD
8 | waste/ Hazardous waste | Capacity Building, Database, TA (National and International Consultants) regarding international conventions and HW n ports
9 | Indistrial Emission | Capacity Building, TA through (National and International Consultants)
10 | Climate changes
11 | Public participation/public awarness