## H2020_RM_plan
Objective | Action/Priorities | Responsible | Expected Output | Potential Sources of funding | Milestone/Target | Progress Indicator
To enhance optimal national information systems allowing for systemic production of indicator-based reporting and sharing of data | Undertake capacity building on systemic data production, statistics, reporting and data sharing | EEA-UNEP/MAP | Regular delivery and sharing of harmonised dataset on annual basis Common repository, QA/QC established Improved National and regional SEIS compliant H2020 Information systems | EU (EIONET, ENI, IPA) UNEP/MAP | At least 90% complete dataflow for IND 1-6 by 2018 50% scoring for new indicators (marine litter, HZ waste) by 2019 Reporting tools efficiently supporting all data flows | % of MPC delivering/sharing expected datasets
| Maintain and improve efficiency of existing data flows (incl. PRTR), and support creation of relevant new data flows and QA/QC procedures based on expanded H2020 issues (Ecosystem approach) | MPC with support from EEA, UNEP/MAP |  | EU (EIONET, ENI, IPA, Twining, TAIEX, bilateral assistance), UNEP/MAP National budget Other bilateral and international donors
Foster the developemnt and management of IT systems (infrastructure for data, automation, reporting tools reportenet/InfoMAP)
Expand indicator managementand and data services (national and regional)
To expand the existing H2020 priorities with a particular focus on water, solid waste and industrial emissions, identify and address additional priority areas | Further refine the current assessment framework in synergie with other regional and national assessemnt process (SOE, ECAP, MSSD, MED2050, MSFD) and test new approaches to better assess in an holistic way water, solid waste and Industrial emissions. Explore ways to address additional priority issues (marine litter, hazardous waste, non-point sources, pollution prevention). | EEA-UNEP/MAP | Updated fachseets IND1-6 and factsheests/methodology for additionnal indicators Country Profile and regional report delivered | EIONET, ENI, IPA, UNEP/MAP | Factsheets elaborated and upgraded by end 2016 23 Country Profiles to be delivered by 2015 (links to NAP evaluation and update, MSSD indicator review) and 2017 (ECAP/SOE preparation, MED 2050 prepartion) Consultation/peer-review of the H2020 report during 2018 Regional Indicator-based assessment delivered by April 2019 | Number of facstheets completed % of Country Profile delivered timely
| Prepare the 2nd indicator-based H2020 assessment report including participatory process/peer review. Support the production of country profile (2015-2017) in synergies with other relevant reportings (NAPs/LBS protocol, ECAP, Regional Plans, MSFD) | MPC with support from EEA, UNEP/MAP |  | EU (EIONET, ENI, IPA, Twining, TAIEX, bilateral assistance), UNEP/MAP National budget
| Undertake capacity building activities on Data Management System and Integrated assessment | EEA-UNEP/MAP |  | EIONET, ENI, IPA, UNEP/MAP Twining, TAEIX Other bilateral and international donors
To ensure the sustainability of the governance setup of the H2020 review processes | Organise regular meeting of the Review and Monitoring group to streer and review the process | Review and Monitoring co-chair | Meetings of the Monitoring and Review sub-group National networking structures (SEIS) operational and efficiently supporting knowledge management | ENI | 1 meeting per year of the RM group with full attendance of MPC and other partners in full coordination with other relevant initiatives and projets or/and as per needed meetings of thematic working groups | % of attendance of MPC
| Institutionalise and integrate existing SEIS/H2020 national committees with clear ToR and regular meetings | MPC with support from EEA, UNEP/MAP |  | National budget EU (EIONET, ENI, IPA), UNEP/MAP
| Support coordination efforts with other national coordination structure and committees (e.g NAPs update) | MPC with support from EEA, UNEP/MAP |  | National budget EU (EIONET, ENI, IPA), UNEP/MAP
| Ensure strong synergies with Research, CB and PRPI components (sub-group leaders coordination meeting, cross consultation of sub-group FPs, exchange of experiences) | Review and Monitoring co-chair MPC |  | ENI
All these priorities actions will be adressed in a context of country visits
MPC: Mediterranean Partner Country comprise Mediterranean EU member states, Western Balkan countries, Turkey, ENP-South countries

## Workplan
| 2017 | [7 empty] | 2018 | [11 empty] | 2019
| May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | August | September | October | November | December
Work plan (June2017 - December 2019) | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
WP1 - In country support
Preparation of in-country support | bar: 2017 May to 2017 Sep
Set-up SEIS national team | bar: 2017 May
Finalised national work plan | bar: 2017 May
Agreement/signature of SSFA; recruitement of national assisstant | bar: 2017 Jun to 2017 Aug
Country visits - Stakeholder engagement (WS1) | bar: 2017 Jul to 2017 Oct
Country visits - Stakeholder engagement (WS2) - pilots | bar: 2017 Sep to 2018 Feb
Implementation of National Work Plans | bar: 2017 Jun to 2019 December
PRTR
Regional PRTR guidelines | bar: 2017 Jul to 2017 Sep
Template for draft legislation | bar: 2017 Jul to 2017 Aug
Country pilots (incl. National workshop) | bar: 2017 Sep to 2019 July
WP2 - Indicators and assessments
Review of H2020 Indicators | bar: 2017 May to 2017 Nov
Refine H2020 assessment framework (outline of country fiches, indicators assessment) | bar: 2017 Jun to 2018 Feb
Developp revised indicator specifications (methodological guidance) | bar: 2017 Jul to 2018 Feb
Test new indicators | bar: 2017 Oct to 2018 Mar
Outline of 2nd H2020 indicator-based assessment (incl country fiches) | bar: 2017 Jun to 2018 Mar
Data handling & data analysis | bar: 2017 Sep to 2018 Aug
Writting, overall coordination with other authors | bar: 2018 Jan to 2018 Dec
Peer review | bar: 2018 Jul to 2018 Sep
Final H2020 report ready for editing / translation / production | bar: 2018 Sep to 2018 Nov; 2019 Apr
Communication/dessimination | bar: 2019 Mar to 2019 October
Undertake capacity building on Indicator and assessment | bar: 2017 Oct to 2019 July
WP3 - Data and statistics
Assessement of current data reporting and quality assurance systems | bar: 2017 Jul to 2017 Dec
Guidelines for data production | bar: 2017 Jul to 2017 Nov
Data collection of H2020 indicators | bar: 2017 Sep to 2018 Jun
Undertake capacity building on data production
WP4 - Infrastructure & data management
Identification of the state of national database infrastructure for SDI and data management | bar: 2017 May to 2017 Aug
Online survey for the identification of national databases and state of the SDI | bar: 2017 May to 2017 Aug
Building the catalogue of metadata | bar: 2017 Jul to 2017 Aug
Setting the INFO MAP for new data reporting | bar: 2017 May to 2018 Mar
Definition of XML schema and data dictionary for the selected ECAP | bar: 2017 May to 2017 Aug
Support PRTR developemnt | bar: 2017 Sep to 2018 Mar
Extension of MEDPOL Information System to include marine litter H2020 indicators | bar: 2017 May to 2018 Mar
Revision and adjustment to the regional data infrastructure for monitoring data flows for the new data reporting | bar: 2017 Jun to 2018 Mar
Implementation of software procedures for indicator calculation | bar: 2018 Apr to 2019 December
Development of data policy documents at country level, in support of common regional standards | bar: 2017 Sep to 2018 Mar
Analysis of the metadata catalogue and advice on data policy at country level | bar: 2017 Sep to 2018 Mar
SDI initiated and developed at country level | bar: 2017 May to 2018 Mar
Implementation of SDI platform at country level | bar: 2017 May to 2017 Dec
Training of national experts to use SDI and reporting infrastructure | bar: 2017 Aug to 2018 Mar
Customisation of citizen science application | bar: 2018 Feb to 2018 Mar
Information layers and data visualisation | bar: 2018 Feb to 2019 December
WP5 - Communication & visibility
Project website population/maintenance
Newsletters (biannual) | bar: 2017 Jul; 2017 Dec; 2018 Jul; 2018 Dec; 2019 July; 2019 December
Side events | bar: 2017 Oct; 2017 Dec
WP6 - Management and coordination
Project Management Group meeting | bar: 2017 Jun; 2017 Oct; 2018 Feb; 2018 Jun; 2018 Oct; 2019 Feb; 2019 June; 2019 October
Annual steering committee meetings | bar: 2017 Oct; 2018 Oct; 2019 October
H2020 coordination group / Review and Monitoring group meetings | bar: 2017 Oct; 2018 Oct; 2019 October
Eionet Mediterranean coordination group | bar: 2017 May; 2017 Oct; 2018 Feb; 2018 Jun; 2018 Oct; 2019 Mar; 2019 June; 2019 October

## OVI
| Intervention logic | Objectively verifiable indicators of achievement | Progress Y1 | Sources and means of verification
Activities | WP1. In-Country support: enhance the national capacities by addressing particular national needs and contribute to regional coherence. | WP1. National work plans between key national stakeholders on sharing and use of environmental data and indicators agreed. | Draft IL, JO, LB, PS, TN prepared and presented at SCM, Dec 2016 SSFA under preparation | Draft NWP
|  | WP1. Monitoring reports on implementation of the work plans presented to the project Steering committee annually. | Done | PPPT, 1st SCM, Dec 2016
| WP2. Indicators and Assessments: ensure regular production of indicators, agreed at regional level under ENPI-SEIS project, and indicator-based assessments relevant to inform and monitor progress of the Horizon 2020 Initiative and contribute to achieving the objectives of the other work packages. | WP2. Methodological documents and national assessments/outlooks on the H2020 priority areas regularly produced. | To start in Y2
|  | WP2. Countries’ contribution to the 2nd regional indicator-based H2020 report (scheduled for 2019). | NA
|  | WP2. National assessments/country briefings included in the 2019 regional report. | NA
| WP3. Data and statistics: ensure timely production and sharing of harmonised, quality assessed statistics and data related to Horizon 2020 thematic priorities. | WP3. Produced data and statistics documented in reports from workshops and technical assistance visits. | NA
|  | WP.3 Number of datasets published and/or available online. | NA
|  | WP3. Guidance/methodological documents produced on the priority areas addressed. | NA
| WP4. Infrastructure and data management: establish and maintain national and regional environmental information systems and data sharing in line with SEIS establishment. | WP4. Environmental indicators and data made available online and regularly/annually updated by EEA and UNEP/MAP, including also information on national websites. | NA
|  | WP4. Meeting reports documenting the countries’ progress in data sharing and exchange, reporting tools and formats used, as well as QA/QC aspects. | H2020 progress IL, LB, PS | 1st SCM, Dec 2016
|  | WP4. National PRTR pilots extended to more industries; PRTR guidelines validated at dedicated regional event(s); catalogue of PRTR good practices in the region created. | NA
| WP5. Visibility and communication: ensure high visibility of the EU support in the actions implemented and active communication with the key project partners and beyond. | WP5. Project outputs and communication materials produced, made available online and shared at relevant regional and national events (reported also in the progress reports annually). | Leaflet 4EN, FR, AR) Project Website 1st project Newsletter (March 2017) Arab WG on Indicators, March 2017
|  | WP5. Contribution to newsletters/info materials of other key regional partners provided on regular basis. | Contribution to UNSD Dec 2016 edition Revamping H2020 MEP website
|  | WP5. Organisation of SEIS-awareness raising and side events linked to relevant regional and/national meetings. | EG country visit, Nov 2016 3 side events planned in 2017
| WP6. Coordination and management: ensure effective and smooth implementation of the project activities, including project management and administration, as well as regular coordination with relevant partners and initiatives. | WP6. Regular meetings/teleconferences with the Contracting Authority on the project implementation. | VC 30/08/2016 Meeting 15/03/2017 | Summary minutes
|  | WP6. Regular (annual) Project Steering Committee meetings held. | Jointly with 7th H2020 RM group meeting, 12-14/12/2016, Athens | Summary minutes
|  | WP6. Regular dialogue/contact with the H2020 coordination group and among the H2020 groups and their chairs. | H2020 Core Group, 28/09/2016 H2020 Core Group, 13/03/2017 PRPI, June 2016, April 2017 SWIM/H2020 SC, Sept 2016
|  | WP6. Number of joint meeting with other regional projects/initiatives. | SCM jointly with RM group meeting